## Work Inventory
sample for each tech stack |  | Status | Target | Demo version |  | Status
1 | sample firebase account creation | Completed |  | 1 | Actual firebase account creation | Not started
2 | sample ionic capacitor project setup | Completed |  | 2 | Actual ionic capacitor project setup | Not started
3 | add android platform | Completed | 2024-03-30 | 3 | add android platform | Not started
4 | create a sample ui page | Completed | 2024-03-30 | 4 | create a sample ui page | Not started
5 | add camera related plugin | Completed | 2024-03-30 | 5 | add camera related plugin | Not started
6 | access camera functionlaity | Completed | 2024-03-30 | 6 | access camera functionlaity | Not started
7 | add tensor flow in sample project | Not started | 2024-03-30 | 7 | add tensor flow in sample project | Not started
8 | use of tensorflow | Not started | 2024-03-30 | 8 | use of tensorflow | Not started
9 | add audio record feature in capacitor | Not started | 2024-03-31 | 9 | add audio record feature in capacitor | Not started
10 | convert audio to english sentence | Not started | 2024-03-31 | 10 | convert audio to english sentence | Not started
11 | convert user sentence to predefine sentence | Not started | 2024-03-31 | 11 | convert user sentence to predefine sentence | Not started
12 | get respective answer and play sound | Not started | 2024-03-31 | 12 | get respective answer and play sound | Not started

## Time Line
| Status | start date | end date
Prepare Idea and finalize | Completed
Requirement analysis | Completed
Requirement note preparation | Completed
tech analysis | Completed
tech stack finalize | Completed
sample for each tech stack | In Progress | 2024-03-29 | 2024-04-01
prepare project setup | In Progress | 2024-03-29 | 2024-04-01
prepare demo verion spec | Not Started | 31-04-2024 | 2024-04-01
develop demo version | Not Started | 2024-04-02 | 2024-04-04
prepare spec for full development | Not Started | 2024-04-05 | 2024-04-05
full application development | Not Started | 2024-04-06 | 2024-04-09
testing of application | Not Started | 2024-04-10 | 2024-04-12
report preparation | Not Started | 2024-04-05 | 2024-04-10
submission | Not Started | 2024-04-14 | 2024-04-15

## Tech Stack
tech | version
Node js | 20.11.1
NVM | 1.1.12
ionic | 7.2.0
capacitor | 5.7.4
react js | 18.2.0
firebase | 13.5.0
android | 7.0 - 14.0
android studio | 2023.2.1